## POM
Market | Retailer | Status | Current phase | Discovery | Build & integration | UAT | Go-live / ETA | Notes
NA | Regional rollout | Live | Live |  |  |  | Mar 2026 | Live in production.
EMEA | Regional rollout | Live | Live |  |  |  | 26 Mar 2026 | Live in production.
APAC | Regional rollout | Live | Live |  |  |  | 23 Mar 2026 | Live in production.
LATAM | Regional rollout | Pending | UAT |  |  |  | TBD | Pending business sign-off; UAT to complete week of 16-Jun.
NA-CA | Regional rollout | Pending | Discovery |  |  |  | TBD | New source data pending (Ana Fuentes).

## TPO
Market | Retailer | Status | Current phase | Discovery | Build & integration | UAT | Go-live / ETA | Notes
CA | Shoppers Drug Mart | Live | Live |  |  |  | May 2026 | Live in production.
DE | Rossmann | Delayed | Build & integration |  |  |  | TBD | Data engineering delay; target date TBD.
DE | Edeka | Delayed | Build & integration |  |  |  | TBD | Data engineering delay; target date TBD.
DE | Rewe | Delayed | Build & integration |  |  |  | TBD | Data engineering delay; target date TBD.
AUS | Coles | Pending | Discovery |  |  |  | TBD | Scope to be confirmed.
AUS | Woolworths | Planned | Build & integration |  |  |  | Jul 2026 | TPO DS Optimized Model under finalization.
UK | Boots | Planned | Build & integration |  |  |  | Sep 2026 | Planned on schedule.
UK | Asda | Planned | Build & integration |  |  |  | Sep 2026 | Planned on schedule.
UK | Tesco | In progress | Build & integration |  |  |  | Jun 2026 | Decision pending on UK Promo Data Transformation.
FR | Carrefour | Planned | Discovery |  |  |  | Oct 2026 | Planned on schedule.
FR | Leclerc | Planned | Discovery |  |  |  | Oct 2026 | Planned on schedule.
FR | Intermarche | Planned | Discovery |  |  |  | Oct 2026 | Planned on schedule.
BR | Droga Raia | Pending | Discovery |  |  |  | TBD | Date TBD.
CHI | AS Watson | In progress | UAT |  |  | 22-29 Jun 2026 | Jul 2026 | PEA go-live first week of July; UAT 22-29 Jun.

## PEA
Market | Retailer | Status | Current phase | Discovery | Build & integration | UAT | Go-live / ETA | Notes
CA | Shoppers Drug Mart | Live | Live |  |  |  | 7 May 2026 | Live in production.
AUS | Woolworths | Live | Live |  |  |  | May 2026 | Live in production.
DE | Rossmann | Delayed | Build & integration |  |  |  | TBD | Data engineering delay; target date TBD.
DE | Edeka | Delayed | Build & integration |  |  |  | TBD | Data engineering delay; target date TBD.
DE | Rewe | Delayed | Build & integration |  |  |  | TBD | Data engineering delay; target date TBD.
AUS | Coles | Planned | Build & integration |  |  |  | Jul 2026 | Planned on schedule.
UK | Boots | Planned | Build & integration |  |  |  | Jun 2026 | Planned on schedule.
UK | Asda | Planned | Build & integration |  |  |  | Jun 2026 | Planned on schedule.
UK | Tesco | In progress | Build & integration |  |  |  | Jun 2026 | Decision pending on UK Promo Data Transformation.
FR | Carrefour | Planned | Discovery |  |  |  | Jul 2026 | Planned on schedule.
FR | Leclerc | Planned | Discovery |  |  |  | Jul 2026 | Planned on schedule.
FR | Intermarche | Planned | Discovery |  |  |  | Jul 2026 | Planned on schedule.
BR | Droga Raia | Pending | Discovery |  |  |  | TBD | Date TBD.
CHI | AS Watson | In progress | UAT |  |  | 22-29 Jun 2026 | Jul 2026 | Go-live first week of July (revised); UAT 22-29 Jun.

## US Customer PnL
Market | Retailer | Status | Current phase | Discovery | Build & integration | UAT | Go-live / ETA | Notes
NA | Discovery & business requirements | Live | Live |  |  |  | 6 May 2026 | 37 of 38 KPIs closed.
NA | Data modelling | Live | Live |  |  |  | 6 May 2026 | Completed.
NA | Tactical build | In progress | Build & integration |  |  |  | Jul 2026 | In progress.
NA | Technical go-live | Planned | UAT |  |  |  | Sep 2026 | UAT, automation and deployment.
NA | Activation | Planned | Discovery |  |  |  | Oct 2026 | Phased expansion to next 8 customers.

## Pricing
Market | Retailer | Status | Current phase | Discovery | Build & integration | UAT | Go-live / ETA | Notes
UK | UK pricing | In progress | Discovery |  |  |  | TBD | Semantic inclusion underway (Adil / Jason).
BR | Brazil pricing datasets | In progress | Discovery |  |  |  | TBD | Datasets in discussion with local DnA; targeted end-May.

## How to use
RGM Program Tracker v2 — how to use
Structure
One tab per product. One row = one deployment. Add rows freely. Don't rename or reorder columns — the dashboard reads by position.
Columns
Market | Region or country code: NA, EMEA, APAC, LATAM, NA-CA, CA, DE, AUS, UK, FR, BR, CHI.
Retailer | Retailer name (Boots, Tesco) or scope item (Regional rollout, Tactical build).
Status | Dropdown: Live / In progress / Planned / Delayed / Pending. Cell colours automatically.
Current phase | Dropdown: Discovery / Build & integration / UAT / Go-live / Live.
Discovery / Build & integration / UAT | Optional phase dates. Fill as you progress.
Go-live / ETA | Headline date on the dashboard row and in What's next. Use TBD if unknown.
Notes | Short event context only — no feature or functionality detail.
Status values
Live | In production.
In progress | Actively in UAT, build, or discussion.
Planned | Scoped, future date, not started.
Delayed | Target date missed or at risk of slipping.
Pending | Awaiting sign-off or decision — no firm date.
Data as of
Week ending 6/5. Update this note each week alongside the data.